## Ark1
GO:WORK |  | Nice to have |  |  | TIMER BRUGT TOM d.20.09
Edit ordre | 2 | Ugenr | 2.5 |  | 13.09 | 4
View aktive Bestillinger | 1 | Dialog box | 1.5 |  | 18.09 | 2
View færdige Bestillinger | 1 | Opret kunde admin area- husk unique code | 2.5 |  | 19.09 | 5
Edit validation snak og implementering | 1.5 | Only display fakultet if relevant | 2 |  | 20.09 | 7
Marker som "booket" checkbox | 1 | Autocomplete
Search box (AJAX/PHP?) | 3 | Log out after inactive? |  |  | Registrering timer
Sort by all fields | 4 |  |  |  | 23.09 | 5
Default sort by date | 2 |  |  |  | 25.09 | 4.5
Automatic mark as completed | 3 |  |  |  | 26.09 | 2
Oprettelsesdato + sort by | 2 |  |  |  | 27.09 | 5
View aktive ordrer table | 1.5 |  |  |  | 2019-09-30 | 1.5
View færdige ordrer table | 1.5 |  |  |  | 2019-10-01 | 2.5
[5 empty] | 2019-10-02 | 3
KUNDER |  |  |  |  | 2019-10-03 | 2.5
View bestillinger per konto | 2 |  |  |  | 2019-10-04 | 5.5
Insert into School info table | 1.5 |  |  |  | 2019-10-07 | 4.5
Insert into accounts table | 1 |  |  |  | 2019-10-09 | 5.5
Insert validation snak og implementering | 2 |  |  |  | 2019-10-10 | 4.5
Send to "KLADER" | 1 |  |  |  | 2019-10-11 | 5.5
Search box (AJAX/PHP?) | 2 |  |  |  | 2019-10-14 | 5
Sort by all fields | 3 |  |  |  | 2019-10-15 | 5.5
Default sort by date | 2 |  |  |  | 2019-10-16 | 5.5
[5 empty] | 2019-10-17 | 3
KLADER |  |  |  |  | 2019-10-21 | 5.5
View bestillinger per konto | 1.5 |  |  |  | 2019-10-22 | 1
Edit ordre | 1.5 |  |  |  | 2019-10-29 | 4
Marker som "færdig" checkbox | 1 |  |  |  | 2019-10-31 | 3
KLADER table | 2 |  |  |  | 2019-11-04 | 1.5
Search box (AJAX/PHP?) | 2
Sort by all fields | 3
Default sort by date | 2 | LEFT TO DO
Validation Date >30 dage | 2
BUGS
BACKUP |  | Send more than one Kladde to confirmation bug | 2.5
Backup databasen- Find hosting som tilbyder backup. Hostinger, Blue Host | 8
KUNDER
Fjern Home.php-> opret orde.php
UX/UI |  | Fjern show 25/100
Logout | 0.33 | Opret ordre -> ændrigner bliver ikke gemt
Login | 0.33 | Edit Kladde
Logo (alle sider+ login center side) | 0.5 | Font size- > 70%
Display special chars æåø | 0.5 | See uploaded document (see more field?) | 1
Other stuff? Snak m. Ole+JJ | 2
GO:WORK
FEEDBACK + final adjustment | 5 | Mark as complete (button + on login) | 4.5 | on completed orders/ kladder, aktive?,
Fix search fields
I alt | 69.66 | Eksport CSV JJ computer
Fjern Kode og Bestilt den I Excel eksport
BACKUP
|  | Backup databasen- Find hosting som tilbyder backup. Siteground, Hostinger, Blue Host | 4
Nice to have
|  | Dialog box | 1.5
|  | Opret kunde admin area- husk unique code | 2.5
|  | Only display fakultet if relevant | 2
Autocomplete
Log out after inactive?